Click and enter a value from the list of items
Click and enter a value from the list of items
Click and enter a value from the list of items
Click and enter a value from the list of items
## PBS
BCN3D - MOVEO - Robotic ARM					Notes : Column "C" and "I" are automated (formulas) : Don't mess-up with them ! . / CC BY-SA Wintergatan
PBS #	NAME	FROZEN	TYPE	BUILD	QUANTITY	CAD ISSUE	STATUS	PROJECT OWNER	COMMENT
#000-000	BCND3D - MOVEO		A - ASSEMBLY				P - DESIGN IN PROGRESS		YOUR WHOLE PROJECT
#100-000	TOP-LEVEL ASSEMBLY 1		A - ASSEMBLY				P - DESIGN IN PROGRESS	DESIGNER	THIS IS THE HIGHEST LEVEL ASSEMBLY...
#110-000	MAIN ASSEMBLY 1		A - ASSEMBLY			YES	A - ASSEMBLED	-	...AND THIS IS ONE LEVEL LOWER...
#110-001	FRONT		D - DESIGNED PART	M - MANUAL MACHINING	1		N - NOT DESIGNED	YOU : CONCEPT	THIS IS A PART WHICH DESIGN WAS NOT STARTED YET
#110-002	BACK		D - DESIGNED PART	M - MANUAL MACHINING	1		P - DESIGN IN PROGRESS	DESIGNER	THIS IS A DESIGN IN PROGRESS
#110-003	RIGHT LOWER HORIZONTAL		D - DESIGNED PART		2		D - DESIGNED	PURCHASER	THIS DESIGN MUST BE PREPARED FOR ORDER.
#110-004	LEFT LOWER HORIZONTAL		D - DESIGNED PART		1		RO - READY TO ORDER	PURCHASER	THIS PART SHOULD BE ORDERED RIGHT NOW.
#110-005	RIGHT UPPER HORIZONTAL		D - DESIGNED PART		1		O - ORDERED	YOU : RECEIVE?	THIS PART IS BEING DELIVERED
#110-006	LEFT UPPER HORIZONTAL		D - DESIGNED PART		1		R - RECEIVED	YOU : ASSEMBLE	YOU HAVE RECEIVED THE PART AND CAN ASSEMBLE IT.
#110-007	FEET PLACEHOLDER		D - DESIGNED PART		4		A - ASSEMBLED	-	JOB DONE. CONGRATS!
#110-008	BRACKETS	YES	D - DESIGNED PART		1		A - ASSEMBLED	-
#670-007	M8 WASHER ISO 7089		H - HARDWARE		4		A - ASSEMBLED	-	HARDWARE PART HAVE #6XX-XXX NUMBERS (SEE NEXT SHEET).
#640-803	M8X14 HEX SOCKET HEAD ISO 4762	YES	H - HARDWARE		4		A - ASSEMBLED	-
#120-000	MAIN ASSEMBLY 2		A - ASSEMBLY				N - NOT DESIGNED	YOU : CONCEPT
#121-000	SUB-ASSEMBLY 2.1		A - ASSEMBLY				N - NOT DESIGNED	YOU : CONCEPT	...AND THIS IS OUR LOWEST (BUT YOU COULD GO EVEN DEEPER).
#121-001	SUB-ASSEMBLY 2.1 RANDOM PART					N - NOT DESIGNED	YOU : CONCEPT
#130-000	MAIN ASSEMBLY 3		A - ASSEMBLY				N - NOT DESIGNED	YOU : CONCEPT
				N - NOT DESIGNED	YOU : CONCEPT
#200-000	TOP-LEVEL ASSEMBLY 2		A - ASSEMBLY				N - NOT DESIGNED	YOU : CONCEPT
				N - NOT DESIGNED	YOU : CONCEPT
#300-000	TOP-LEVEL ASSEMBLY 3		A - ASSEMBLY				N - NOT DESIGNED	YOU : CONCEPT
				N - NOT DESIGNED	YOU : CONCEPT
#400-000	TOP-LEVEL ASSEMBLY 4		A - ASSEMBLY				N - NOT DESIGNED	YOU : CONCEPT
				N - NOT DESIGNED	YOU : CONCEPT
#500-000	TOP-LEVEL ASSEMBLY 5		A - ASSEMBLY				N - NOT DESIGNED	YOU : CONCEPT
				N - NOT DESIGNED	YOU : CONCEPT

## COMMON
PBS COMMON PARTS					Note : this is where you list parts that will be shared among different assemblies. / It's mostly off-the-shelf parts.
PBS #	NAME	QUANTITY	CAD ISSUE	STATUS	COMMENT
#600-000	COMMON			D - DESIGNED
#610-000	MAGNETS			D - DESIGNED
#610-001	DISC MAGNET 10X2MM	0		D - DESIGNED	This is a standard example of a part used in the design.

#620-000	BEARINGS			D - DESIGNED
#620-001	683 BEARING	0		P - DESIGN IN PROGRESS	This part should not be used yet since it's a Design in Progress

#630-000	SPRINGS			D - DESIGNED
#630-001	?CONVEYER RATCHET SPRING	0		D - DESIGNED	This part is greyed since it's not used in any assemblies (Qty=0)

#640-000	MACHINE SCREWS & BOLTS			D - DESIGNED
#640-301	M3X4 GRUBSCREW ISO 4029	0		RO - READY TO ORDER	This part should be Ordered to replenish our storage : "RO"

#650-000	WOOD SCREWS & SPECIAL SCREWS			D - DESIGNED

#660-000	NUTS			D - DESIGNED

#670-000	WASHERS			D - DESIGNED

#680-000	THREADED RODS			D - DESIGNED

#690-000	INSERTS			D - DESIGNED

#6A0-000	MARBLES			D - DESIGNED

#6B0-000	SPACER			D - DESIGNED

#6C0-000	STOPRING			D - DESIGNED

#6D0-000	MISCELLANEOUS			D - DESIGNED